## Sheet1
Project Title: |  | Tetris Pi
Name of Project Developer: |  | Danylo perkov
Week | Begining | End of | Deadlines | Deadlines | Tasks | Status
No. | of the week | the week |  | dates |  | (Completed, In Progress)
0 | 2022-01-10 | 2022-01-14 |  |  | Design intent defined. | completed
1 | 2022-01-17 | 2022-01-21
2 | 2022-01-24 | 2022-01-28 | Proposal submited. | 2022-01-30 | Project approved. | completed
3 | 2022-01-31 | 2022-02-04 |  |  | Research into the electrical/software side of the project. | completed
4 | 2022-02-07 | 2022-02-11
5 | 2022-02-14 | 2022-02-18
6 | 2022-02-21 | 2022-02-25 |  |  | Complete assembly of the electrical parts of the headset and its testing. | completed
7 | 2022-02-28 | 2022-03-04 |  |  | STUDY BREAK - Main body design/lenses purchase | completed
8 | 2022-03-07 | 2022-03-11 | Evaluation No 1. | 2022-03-07 | Progress review with the supervisor. Review the need for prototype. Design and print of the PCB for the electronic components. | completed
9 | 2022-03-14 | 2022-03-18
10 | 2022-03-21 | 2022-03-25 |  |  | Main body design | completed
11 | 2022-03-28 | 2022-04-01
12 | 2022-04-04 | 2022-04-08
13 | 2022-04-11 | 2022-04-15 |  |  | Main body design & print | completed
14 | 2022-04-18 | 2022-04-22 |  |  | Main body design & print | completed
15 | 2022-04-25 | 2022-04-29
16 | 2022-05-02 | 2022-05-06 | Evaluation No 2. | 2022-04-28 | Review the original design intent and the perforamnce of the device. | completed
17 | 2022-05-09 | 2022-05-13 |  |  | Test the functionality & troubleshooting | completed
18 | 2022-05-16 | 2022-05-20 |  |  | Adjustments, modifications, performance evaluation, assembly. | completed
19 | 2022-05-23 | 2022-05-27 | Formal Presentation + Report |  | Finishing the documentation for the project as well as the other paperwork. | completed